## Read Me
GateFlow AI — Jira-ready backlog (FINAL)
Version / date | v1.2 FINAL · 25 October 2026 · aligned to PRD v2.2 FINAL and MRD v3.2 FINAL
Team | BA: Rathi Sankari S · UI/UX: Sanjay · Developer: Abishek Edwin Raj · QA: Venkatesan
Kickoff gate | 3–5 epics and 8–15 stories with acceptance criteria that trace to the PRD. This backlog: 4 epics, 15 stories. Future items sit on the “Out of scope” sheet, not as stories.
IDs | EP-, ST-, SUB- and TC- are documentation IDs, not Jira issue keys. No sprints or Jira states are invented.
Status source | Developer’s Prototype Implementation Handover. “Implemented and tested” = exercised by the reproduced local API run. API evidence is not proof of the browser demo; see TC-14. QA reports testing complete, but individual TC results have not been supplied, so none is marked Pass.
Data | All results come from the synthetic Oakridge Academy scenario. None is field-measured.
Jira import | Stories: User story → Summary; Acceptance criteria → Description; Epic ID → Epic Link; PRD requirements → custom field.
Stories by implementation status
Implemented and tested | 3
Implemented, testing incomplete | 6
Pending confirmation | 6
Total stories | 15
Tests passed (from Test checklist) | 0
Tests failed | 0
Test results not supplied | 16

## Epics
Epic ID | Name | Business outcome | Scope | Priority | Dependencies | Definition of done | PRD requirements | MRD needs
EP-01 | Diagnose the bottleneck (Must-Have M1) | Users see the school and which gate and cohort cause the dismissal bottleneck | Load synthetic scenario; overview; file-backed map annotations; rule-based diagnosis | Must | None | Overview shows 4 gates, 5 cohorts, 775 students, 540 vehicles; bottleneck named with its rule | FR-01 – FR-04 | N2, N4
EP-02 | Plan within school rules (Must-Have M2) | Users get timing and gate plans that respect fixed rules | Plain-text constraint parsing; kindergarten in fixedGroups; sibling sync; eligibility and capacity; bounded enumeration; Pareto filter; no-feasible message | Must | EP-01 | All rule tests pass; counts shown; only non-dominated candidates returned | FR-05 – FR-10, FR-14 | N1
EP-03 | Compare and stress-test (Must-Have M3) | Users compare current and candidate plans fairly, including under stress | Same-run deterministic comparison; six stress cases; synthetic labels; repeatability | Must | EP-02 | Same-run values for queue, p95 wait, delay; six cases; labelled synthetic; identical on rerun | FR-11 – FR-13, NFR-01 | N3, N4
EP-04 | Demo readiness | The team shows the working prototype reliably in the 15-minute slot | Demo login; offline run; README; backup recording | Required hand-in (not a product Must-Have) | EP-01 – EP-03 | PRD section 14 checklist fully ticked | FR-15, NFR-02, NFR-03 | Kickoff hand-ins

## Stories
Story ID | Epic ID | User story | Priority | Implementation status (evidence-based) | Dependencies | Acceptance criteria (Given / When / Then) | PRD requirements | Demo evidence / validation method
ST-01 | EP-01 | As a school administrator, I want an overview of the school scenario, so that I know what I am planning for. | Must | Implemented, testing incomplete (scenario load tested in reproduced run; overview screen and baseline label pending confirmation) | — | Given the app is running When I open Scenario Overview Then it shows 4 gates, 5 cohorts, 775 students and 540 vehicles with gate annotations And the 48-vehicle / 16.4-min baseline is labelled as scenario-provided | FR-01, FR-02, FR-03 | Live demo step 1; QA checklist
ST-02 | EP-01 | As a gate coordinator, I want to see which gate and cohort cause the bottleneck, so that I know where the problem is. | Must | Implemented, testing incomplete (test mapping pending) | ST-01 | Given the scenario is loaded When I open Bottleneck Diagnosis Then the bottleneck gate and cohort are named with the rule that flagged them | FR-04 | Live demo step 2
ST-03 | EP-02 | As a school administrator, I want to enter scheduling rules in plain words, so that I do not need technical settings. | Must | Implemented, testing incomplete (rule/regex parser, no LLM) | ST-01 | Given the Schedule Search screen When I enter supported constraint text Then the parsed rules are applied deterministically to the search | FR-05 | QA test with sample text
ST-04 | EP-02 | As a school administrator, I want kindergarten kept fixed and siblings released together when I choose, so that families’ routines are protected. | Must | Implemented, testing incomplete (conditional) | ST-03 | Given the kindergarten cohort is in fixedGroups and sibling sync is enabled When the search runs Then no candidate changes kindergarten timing And linked cohorts share one release time | FR-06, FR-07 | Live demo step 3; AC-03, AC-04
ST-05 | EP-02 | As a gate coordinator, I want cohorts moved only to eligible gates with capacity, so that plans are workable on the ground. | Must | Implemented and tested (reproduced run) | ST-01 | Given gate eligibility and capacity in the scenario When the search runs Then no candidate uses an ineligible gate And over-capacity combinations are infeasible | FR-08, FR-09 | AC-05; reproduced run
ST-06 | EP-02 | As a school administrator, I want only the best trade-off plans, with search counts, so that I can see what was considered. | Must | Implemented and tested (reproduced run) | ST-03 – ST-05 | Given the demo scenario and rules When the search runs Then evaluated, feasible, infeasible and dominated counts are shown And every returned candidate is non-dominated (Reproduced: 2,662 / 1,331 / 1,331 / 1,330; 1 candidate) | FR-09, FR-10 | AC-06; live demo step 3
ST-07 | EP-02 | As a school administrator, I want to be told when no plan satisfies my rules, so that I know which rule to relax. | Must | Pending confirmation | ST-06 | Given rules no combination satisfies When the search runs Then the screen says no feasible candidate exists and names the blocking rule | FR-14 | AC-11; QA test with an impossible rule
ST-08 | EP-03 | As a school administrator, I want the current and candidate plans compared in the same run, so that the comparison is fair. | Must | Implemented and tested (reproduced run) | ST-06 | Given a candidate When the comparison runs Then modelled queue, p95 wait and total delay come from one deterministic run for both And the overview baseline is not shown beside them | FR-11 | AC-07; reproduced 3.8→0 veh, 2.5→0 min, 0.6→0 veh-h (synthetic)
ST-09 | EP-03 | As a school administrator, I want to see how a plan behaves under stress, so that I know whether it survives a bad day. | Must | Implemented, testing incomplete (six case definitions pending) | ST-08 | Given a candidate When stress cases run Then results appear for all six cases And each states its modelled assumption | FR-12 | AC-08; live demo step 5
ST-10 | EP-03 | As a school administrator, I want every result labelled as a synthetic estimate, so that no one mistakes it for measured traffic. | Must | Pending confirmation | ST-08, ST-09 | Given any comparison or stress result When it is displayed Then the screen states “Synthetic deterministic estimate — not field-measured” | FR-13 | AC-10; visual check
ST-11 | EP-03 | As a school administrator, I want identical inputs to give identical results, so that I can rely on a rerun. | Must | Pending confirmation (deterministic by design; repeat-run check not done) | ST-08 | Given identical scenario and rules When search and comparison run twice Then outputs are identical | NFR-01 | AC-09; QA diff of two responses
ST-12 | EP-04 | As a school administrator, I want a quick demo login with a role, so that I can open the workflow. | Could | Implemented, testing incomplete (demo convenience, not production authentication) | — | Given the login screen When a demo role is chosen Then the workflow opens | FR-15 | Live demo start
ST-13 | EP-04 | As a school administrator using the tool at school, I want it to work without internet, so that a poor connection cannot stop it. | Must | Pending confirmation | ST-01 – ST-11 | Given Wi-Fi is off When the full workflow is run in the browser Then every screen works and no external call is attempted | NFR-02 | QA offline run-through
ST-14 | EP-04 | As a judge or new developer, I want to run the app from the README in under 5 minutes, so that I can check the work. | Must | Pending confirmation | ST-13 | Given a fresh clone When I follow the README Then backend and frontend start within 5 minutes | NFR-03 | Timed fresh-clone test (kickoff hand-in)
ST-15 | EP-04 | As a judge, I want a backup recording of the full workflow, so that I can assess the prototype even if the live app fails. | Must | Pending confirmation | ST-10 | Given the recording on the demo laptop When it is played Then it shows Overview → Diagnosis → Search → Comparison → Stress cases with labels visible | NFR-03 | Playback test before 10:00

## Subtasks
Subtask ID | Story ID | Task | Responsible (role — name)
SUB-01 | ST-07 | Return an explicit “no feasible candidate” result with the blocking rule from the search API | Dev — Abishek Edwin Raj
SUB-02 | ST-07 | Show the no-feasible message in Schedule Search | UI/UX — Sanjay
SUB-03 | ST-10 | Add “Synthetic deterministic estimate — not field-measured” to Comparison and Stress screens | UI/UX — Sanjay
SUB-04 | ST-01 | Label the overview baseline (48 vehicles / 16.4 min) as scenario-provided | UI/UX — Sanjay
SUB-05 | ST-09 | Write a one-line definition of each of the six stress cases | BA + Dev — Rathi Sankari S, Abishek Edwin Raj
SUB-06 | ST-04 | Confirm whether plain-text rules fill fixedGroups, or whether kindergarten must be added to fixedGroups directly | Dev — Abishek Edwin Raj
SUB-07 | ST-11 | Run search and comparison twice; diff the responses | QA — Venkatesan
SUB-08 | ST-13 | Full browser run-through with Wi-Fi off | QA — Venkatesan
SUB-09 | ST-14 | Write README start commands; time a fresh-clone start | Dev + QA — Abishek Edwin Raj, Venkatesan
SUB-10 | ST-15 | Record the full workflow; test playback on the demo laptop | UI/UX — Sanjay

## Test checklist
Test ID | Story ID | Check | Result (Pass / Fail / Not run / Result not supplied) | Notes (failure detail, evidence, date) | Tester
TC-01 | ST-01 | AC-01 Overview counts and labelled baseline | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-02 | ST-02 | AC-02 Bottleneck named with rule | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-03 | ST-03 | Supported constraint text is parsed and applied | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-04 | ST-04 | AC-03 Kindergarten unchanged when in fixedGroups | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-05 | ST-04 | AC-04 Linked cohorts share release time when sibling sync on | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-06 | ST-05 | AC-05 No ineligible gate in any candidate | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-07 | ST-06 | AC-06 Counts shown; candidates non-dominated | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-08 | ST-07 | AC-11 No-feasible message with blocking rule | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-09 | ST-08 | AC-07 Same-run comparison; overview baseline not beside it | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-10 | ST-09 | AC-08 Six stress cases produce results | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-11 | ST-10 | AC-10 Synthetic label on every result | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-12 | ST-11 | AC-09 Identical output on rerun | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-13 | ST-12 | Demo login opens the workflow | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-14 | ST-13 | Full workflow with Wi-Fi off | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-15 | ST-14 | Fresh-clone start under 5 minutes | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan
TC-16 | ST-15 | Backup recording plays on the demo laptop | Result not supplied | QA reports testing complete; individual result not yet provided | QA — Venkatesan

## Out of scope
Item (not a backlog story) | PRD ref | Priority | Status | Reason
Import observed gate counts | FR-17 | Should (next release) | Planned / not implemented | Needs a field count first (MRD section 10)
Field validation: gate count and P1/P2 interviews | MRD section 10 | Should (next release) | Planned / not implemented | Research task, not a build story
Vehicle-type pickup zones | FR-16 | Won't (this MVP) | Planned / not implemented | Prototype reassigns gates by cohort
SUMO run of the active scenario | FR-20 | Won't (this MVP) | Planned / not implemented (separate six-group SUMO prototype exists) | Different scenario; not connected
Live traffic (Google Maps / Places) | FR-18 | Won't (this MVP) | Configured but not live-verified (code present) | Demo stays offline
LLM assistance (OpenRouter) | FR-19 | Could | Configured but not live-verified (code present) | Not needed for the decision
Parent notice | FR-21 | Could | Planned / not implemented | Demo ends at plan comparison
Result persistence | FR-22 | Won't (this MVP) | Planned / not implemented | Results held in memory
Production authentication and deployment | PRD section 4 | Won't (this MVP) | Planned / not implemented | Demo login, local run only
Trained ML model | PRD section 1 | Won't (this MVP) | Planned / not implemented | No observed data to learn from

## Traceability
MRD need | PRD feature | PRD requirements | Epics | Stories | Demo metric / tests
N1 Rule-respecting changes | M2 | FR-05 – FR-10, FR-14 | EP-02 | ST-03 – ST-07 | SM2; TC-03 – TC-08
N2 Where congestion builds | M1, M2 | FR-03, FR-04, FR-08 | EP-01, EP-02 | ST-01, ST-02, ST-05 | SM1; TC-01, TC-02, TC-06
N3 Compare before changing | M3 | FR-11, FR-12, NFR-01 | EP-03 | ST-08, ST-09, ST-11 | SM3; TC-09, TC-10, TC-12
N4 Understand results | M1, M3 | FR-01, FR-02, FR-13 | EP-01, EP-03 | ST-01, ST-06, ST-10 | SM1; TC-01, TC-07, TC-11
Demo readiness (kickoff hand-ins) | C1 | FR-15, NFR-02, NFR-03 | EP-04 | ST-12 – ST-15 | SM1; TC-13 – TC-16
N5, N6 (future) | C3, S1 | FR-21, FR-17 | — | Out of scope sheet | —